## general
In progress task number: | 25

## in progress
PSA Task Name | ID | Partner Name | Customer Name | Notes | Date | Contact1 | Contact2 | Implementation Specialist | directions | Specs | EDI ID | Van/AS2/FTP | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23
Testing : Ace Mart : New Trading Partner Setup | 25 | Ace Mart | Twang | 12.13.21 Waiting for the FTP information from trading partner 12.6.21 Reach out to trading partner:2 11.19.21 Reach out to trading partner:1 | 2021-12-13 | andy@cjponyparts.com
Testing : CJ Pony Parts - File Partner : New Trading Partner Setup | 25 | CJ Pony Parts - File Partner | Mishimoto | 12.6.21 Reach out to new contact 11.18.21 Reach out to trading partner:3 11.11.21 Reach out to trading partner:2 11.4.21 Reach out to trading partner | 2021-12-06 | No Contacts
Testing : Cosma - Bowling Green Metalforming : New Trading Partner Setup | 25 | Cosma - Bowling Green Metalforming | National Standard Stillwater | 12.6.21 Waiting for Specs and samples from Magna 11.22.21 Reach out to Brandon for updates 11.12.21 Reach out to Brandon for updates 11.4.21 Waiting for new contact from Brandon 10.25.21 Reach out to Cosma for details again:3 10.17.21 Reach out to Cosma for details again:2 10.8.21 Reach out to Cosma for details again 9.29.21 Wait for reply from Cosma 9.26.21 Reach out to Brandon and confirm again 9.22.21 Reach out to new contact:2 9.10.21 Reach out to new contact 9.3.21 Reach out to Brandon Jones for a new Contact 8.27.21 Reach out to trading partner | 2021-12-06 | jana.iddings@magna.com
Testing : Deutsch Family Wine & Spirits : New Trading Partner Setup | 25 | Deutsch Family Wine & Spirits | Empire Distributors of NC | 12.6.21 submitted a mapping case 11.19.21 Reach out to trading partner:1 | 2021-12-06
Testing : Dynamite Services : New Trading Partner Setup | 25 | Dynamite Services | partner: Dynamite Services | 12.20.21 Testing : Dynamite Services : New Trading Partner Setup | 2021-12-20 | Bevin@dynamiteservices.com
Testing : Elastic- Burton Snowboarding : New Trading Partner Setup | 25 | Elastic- Burton Snowboarding | Burton Snowboards USA | 12.3.21 Waiting for contact, FTP account | 2021-12-03
Testing : Focus First Global Logistics : New Trading Partner Setup | 25 | Focus First Global Logistics | partner: Focus First Global Logistics | 12.20.21 Testing : Focus First Global Logistics : New Trading Partner Setup | 2021-12-20 | anjou@focusfirstglobal.com | joshyingbusiness@gmail.com
Testing : Georges Music XML : New Trading Partner Setup | 25 | Georges Music XML | Gator Cases, Inc | 12.6.21 waiting for the connection method 11.22.21 Reach out to new contact:2 11.16.21 Reach out to customer for contact 11.5.21 Reach out to Aaron for help 10.28.21 Reach out to customer:1 10.20.21 waiting for contact from jodi 10.11.21 Reach out to trading partner: 1 | 2021-12-06 | No Contacts
Testing : Grassmid Transport Inc. : New Trading Partner Setup | 25 | Grassmid Transport Inc. | Frank Brunckhorst Co, LLC | 12.6.21 Reach out to trading partner:2 11.19.21 Reach out to trading partner:1 | 2021-12-06
Testing : GSK Consumer Healthcare - New : New Trading Partner Setup | 25 | GSK Consumer Healthcare - New | partner: GSK Consumer Healthcare - New | 12.7.21 Reach out to trading partner :1 | 2021-12-07
Testing : Guitar Center - XML Trading Partner : New Trading Partner Setup | 25 | Guitar Center - XML Trading Partner | Gator Cases, Inc | 12.6.21 Should put into on hold, confirm with Jodi 11.23.21 Reach out again looking for solution 11.16.21 Communicating with trading partner looking for new connection method 11.8.21 Reach out to Aaron for help 10.29.21 Reach out to new contact 10.21.21 Wait for new contact from Jodi 10.11.21 Reach out to trading partner: 1 | 2021-12-06 | gc@gc.com
Testing : Herregan Distributors Inc. : New Trading Partner Setup | 25 | Herregan Distributors Inc. | Precision Flooring Products | 12.6.21 Reach out to trading partner again and also Brad for help 11.18.21 Waiting for the sample data for mapping 11.11.21 Waiting for the sample data for mapping 11.4.21 Waiting for the updates for connection methods 10.25.21 Waiting for reply for TP 10.18.21 Reach out to trading partner: 2 10.9.21 Reach out to trading partner: 1 | 2021-12-06 | dgartman@gartman.com
Testing : Paragon Sports : New Trading Partner Setup | 25 | Paragon Sports | Burton Snowboards USA | 12.6.21 Reach out to TP:3 11.28.21 Reach out to TP:2 11.19.21 Reach out to trading partner:1 | 2021-12-06 | Multiple Records
Testing : Peg Perego : New Trading Partner Setup | 25 | Peg Perego | Brixy | 12.6.21 Reach out to Larry for a new contact:2 11.29.21 Reach out to Larry for a new contact:1 11.22.21 Reach out to trading partner: 3 11.12.21 Reach out to trading partner:2 11.4.21 Reach out to trading partner | 2021-12-06 | No Contacts
Testing : Pure Country West : New Trading Partner Setup | 25 | Pure Country West | Southwest Indian Foundation | 12.6.21 Reach out to the right person from Migual 11.23.21 Schedule a meeting with trading partner 11.16.21 Reach out to EDI support from Pure Country West 11.5.21 Reach out to Miguel for updates 10.29.21 Reach out to Bill again 10.22.21 Reach out to Bill agian 10.15.21 Reach out to Bill agian 10.8.21 Reach out to Bill again 9.28.21 Waiting for reply from Bill 9.22.21 Reach out to trading partenr:2 9.13.21 Reach out to trading partner | 2021-12-06
Testing : Pure Country West : New Trading Partner Setup | 25 | Pure Country West | Southwest Indian Foundation | 12.6.21 Reach out to the right person from Migual 11.23.21 Schedule a meeting with trading partner 11.16.21 Reach out to EDI support from Pure Country West 11.5.21 Reach out to Miguel for updates 10.29.21 Reach out to Bill again 10.22.21 Reach out to Bill agian 10.15.21 Reach out to Bill agian 10.8.21 Reach out to Bill again 9.28.21 Waiting for reply from Bill 9.22.21 Reach out to trading partenr:2 9.13.21 Reach out to trading partner | 2021-12-06 | mike.palmer@pegperego.com
Testing : Quadratec - Mishimoto - P2P : New Trading Partner Setup | 25 | Quadratec - Mishimoto - P2P | partner: Quadratec - Mishimoto - P2P | 12.7.21 Reach out to IM for transaction types | 2021-12-07
Testing : SC Johnson : New Trading Partner Setup | 25 | SC Johnson | Pharmapacks LLC | 12.6.21 Waiting for AS2 informaiton from TP | 2021-12-06 | rebeccab@purecountry.com
Testing : Schoolisin : New Trading Partner Setup | 25 | Schoolisin | partner: Schoolisin | 12.7.21 Reach out to IM Ryan Radlosky for a TP contact | 2021-12-07
Testing : Ste Michelle Wine Estates : New Trading Partner Setup | 25 | Ste Michelle Wine Estates | Empire Distributors of NC | 12.6.21 Need Cory to inform the situation 11.26.21 Reach out to trading partner:2 11.19.21 Reach out to trading partner:1 | 2021-12-06 | No Contacts
Testing : Thoroughbred Diesel : New Trading Partner Setup | 25 | Thoroughbred Diesel | Mishimoto | 12.6.21 Reach out to new contact 11.18.21 Reach out to trading partner:3 11.11.21 Reach out to trading partner:2 11.4.21 Reach out to trading partner | 2021-12-06
Testing : Thoroughbred Diesel : New Trading Partner Setup | 25 | Thoroughbred Diesel | partner: Thoroughbred Diesel | 12.20.21 Testing : Thoroughbred Diesel : New Trading Partner Setup | 2021-12-20 | cody@viduus.org
Testing : Windsor Modules : New Trading Partner Setup | 25 | Windsor Modules | Thomson Fasteners, Inc - Do Not Use | 12.6.21 Reach out to new contact 11.18.21 Reach out to trading partner: 3 11.11.21 Reach out to trading partner:2 11.4.21 Reach out to trading partner | 2021-12-06
Testing : Windsor Modules : New Trading Partner Setup | 25 | Windsor Modules | Thomson Fasteners, Inc - Do Not Use | 12.6.21 Reach out to new contact 11.18.21 Reach out to trading partner: 3 11.11.21 Reach out to trading partner:2 11.4.21 Reach out to trading partner | 2021-12-06 | cody@viduus.org
Testing : Windsor Modules : New Trading Partner Setup | 25 | Windsor Modules | Thomson Fasteners, Inc - Do Not Use | 12.6.21 Reach out to new contact 11.18.21 Reach out to trading partner: 3 11.11.21 Reach out to trading partner:2 11.4.21 Reach out to trading partner | 2021-12-06
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #VALUE!
| 25 | #VALUE! | #VALUE! |  | #REF!
| 25 | #VALUE! | #VALUE! |  | #REF!
Formulas:
Date = DATEVALUE(SUBSTITUTE(LEFT(Table2[[#This Row],[Notes]],SEARCH(" ",Table2[[#This Row],[Notes]])-1),".","/"))
Notes = IF([Partner Name]="done",TEXT(TODAY(),"m.d.yy")&" Reach out to trading partner",TEXT(TODAY(),"m.d.yy")&" "&[PSA Task Name])

## pending
PSA Task Name | Customer Name | Partner Name | Notes | Date | Contact | Email | Column1 | directions | Specs | EDI ID | Van/AS2/FTP | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23
Testing : Akron Generics : New Trading Partner Setup | 170901564 | Micro Labs USA, Inc. | 12.13.21 Reach out to trading partner: 2 12.8.21 Reach out to trading partner: 1
Testing : CJ Pony Parts - File Partner : New Trading Partner Setup | 165975297 | Mishimoto | 12.20.21 Reach out to new contact:3 12.13.21 Reach out to new contact:2 12.6.21 Reach out to new contact 11.18.21 Reach out to trading partner:3 11.11.21 Reach out to trading partner:2 11.4.21 Reach out to trading partner
Testing : Crutchfield : New Trading Partner Setup | 171057145 | Boss Audio Systems | 12.20.21 submitted a mapping case: 14082304 12.13.21 Reaching out to Larry for contact from Crutchfield 12.8.21 Reaching out to Larry for contact from Crutchfield
Testing : Dignity Health : New Trading Partner Setup | 172250745 | Nephron Pharmaceuticals | 12.17.21 Reach out to TP: 1
Testing : Dynamite Services : New Trading Partner Setup | 169234325 | JH Specialties Inc. | 12.20.21 Reach out to trading partner:3 12.14.21 Reach out to trading partner:2 12.7.21 Reach out to trading partner:1
Testing : Focus First Global Logistics : New Trading Partner Setup | 170053143 | Princess Polly | 12.20.21 Reach out TP for updates 12.14.21 Reach out to TP for updates 12.7.21 Reach out to TP
Testing : Georges Music XML : New Trading Partner Setup | 164761814 | Gator Cases, Inc | 12.20.21 Reaching out to Neal again 12.6.21 waiting for the connection method 11.22.21 Reach out to new contact:2 11.16.21 Reach out to customer for contact 11.5.21 Reach out to Aaron for help 10.28.21 Reach out to customer:1 10.20.21 waiting for contact from jodi 10.11.21 Reach out to trading partner: 1
Testing : Golden State Medical Supply : New Trading Partner Setup | 172071864 | Amici Pharmaceuticals | 12.17.21 Reach out to TP:1
Testing : Grassmid Transport Inc. : New Trading Partner Setup | 166674194 | Frank Brunckhorst Co, LLC | 12.20.21 Waiting for the updates from TP 12.13.21 Reach out to trading partner:3 12.6.21 Reach out to trading partner:2 11.19.21 Reach out to trading partner:1
Testing : Herregan Distributors Inc. : New Trading Partner Setup | 153022624 | Precision Flooring Products | 12.20.21 Reach out to David for updates:2 12.15.21 Reach out to David for updates 12.6.21 Reach out to trading partner again and also Brad for help 11.18.21 Waiting for the sample data for mapping 11.11.21 Waiting for the sample data for mapping 11.4.21 Waiting for the updates for connection methods 10.25.21 Waiting for reply for TP 10.18.21 Reach out to trading partner: 2 10.9.21 Reach out to trading partner: 1
Testing : HTL-Strefa -P2P- Avmedical : New Trading Partner Setup | 170837436 | HTL-Strefa, Inc. | 12.20.21 submitted a mapping case: 14082414 12.15.21 waiting for transaction types from Jennifer
Testing : Imperial Data Vendor : New Trading Partner Setup | 171688347 | Genuine Supply | 12.17.21 Reach out to TP:1
Testing : Le Mars Public Storage : New Trading Partner Setup | 170887330 | The Foreign Candy Co Inc | 12.20.21 Reach out to tracy and customer for updates 12.7.21 Waiting for IM
Testing : Philips Products : New Trading Partner Setup | 171819498 | Carewell | 12.17.21 Reach out to TP:1
Testing : Pure Country West : New Trading Partner Setup | 161048210 | Southwest Indian Foundation | 12.15.21Reach out to the right person from Migual 12.6.21 Reach out to the right person from Migual 11.23.21 Schedule a meeting with trading partner 11.16.21 Reach out to EDI support from Pure Country West 11.5.21 Reach out to Miguel for updates 10.29.21 Reach out to Bill again 10.22.21 Reach out to Bill agian 10.15.21 Reach out to Bill agian 10.8.21 Reach out to Bill again 9.28.21 Waiting for reply from Bill 9.22.21 Reach out to trading partenr:2 9.13.21 Reach out to trading partner
Testing : Pure Country West : New Trading Partner Setup | 163403180 | Southwest Indian Foundation | 12.6.21 Reach out to the right person from Migual 11.23.21 Schedule a meeting with trading partner 11.16.21 Reach out to EDI support from Pure Country West 11.5.21 Reach out to Miguel for updates 10.29.21 Reach out to Bill again 10.22.21 Reach out to Bill agian 10.15.21 Reach out to Bill agian 10.8.21 Reach out to Bill again 9.28.21 Waiting for reply from Bill 9.22.21 Reach out to trading partenr:2 9.13.21 Reach out to trading partner
Testing : Quadratec - Mishimoto - P2P : New Trading Partner Setup | 170464367 | Mishimoto | 12.20.21 Waiting for updates from customer 12.7.21 Reach out to IM for transaction types
Testing : Schoolisin : New Trading Partner Setup | 169791463 | Vcom IMC | 12.15.21 Reach out to IM Ryan Radlosky for a TP contact 12.7.21 Reach out to IM Ryan Radlosky for a TP contact
Testing : Ste Michelle Wine Estates : New Trading Partner Setup | 165270972 | Empire Distributors of NC | 12.6.21 Need Cory to inform the situation 11.26.21 Reach out to trading partner:2 11.19.21 Reach out to trading partner:1
Testing : Thayer : New Trading Partner Setup | 172242824 | Old Dominion Peanut Company
Testing : Thoroughbred Diesel : New Trading Partner Setup | 165975109 | Mishimoto | 12.6.21 Reach out to new contact 11.18.21 Reach out to trading partner:3 11.11.21 Reach out to trading partner:2 11.4.21 Reach out to trading partner
Testing : Thoroughbred Diesel : New Trading Partner Setup | 170028751 | Interior Define | 12.6.21 Reach out to new contact 11.18.21 Reach out to trading partner:3 11.11.21 Reach out to trading partner:2 11.4.21 Reach out to trading partner
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE!
| #VALUE! | #VALUE!

## completed
PSA Task Name | Customer Name | Partner Name | Notes | Date | Contact | Email | Column1 | directions | Specs | EDI ID | Van/AS2/FTP | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23
Testing : Full Compass : New Trading Partner Setup |  | Full Compass | partner: Full Compass | #REF! | compliance@dicentral.com
Testing : Raynor Gaming : New Trading Partner Setup | Raynor Gaming | Raynor Gaming | 11.3.21 Reach out to new contact:2 10.22.21 Reach out to the new contact 10.15.21 Ask Brad for a new contact 10.8.21 Reach out to TP:3 9.26.21 Reach out to TP:2 9.17.21 Reach out to trading partner | 2021-12-20 | dgrossman@raynorgroup.com
Testing : C2wireless SPS Vendor : New Trading Partner Setup | C2wireless SPS Vendor | C2wireless SPS Vendor | 11.4.21 Still need directions for these two transactions 10.25.21 Reach out to trading partner again for update 10.14.21 Waiting for the updates 10.8.21 Reach out to trading partner:2 9.27.21 Reaching out to trading partner | 2021-12-20 | Cstokes@c2wdistribution.com
Testing : Cameron Ashley Building Products, Inc. : New Trading Partner Setup | Cameron Ashley Building Products, Inc. | Cameron Ashley Building Products, Inc. | 11.4.21 Reach out to new contact 10.27.21 No Contacts | 2021-12-20 | No Contacts
Testing : CJ Pony Parts - File Partner : New Trading Partner Setup | CJ Pony Parts - File Partner | CJ Pony Parts - File Partner | 11.4.21 Reach out to trading partner | 2021-12-20 | andy@cjponyparts.com
Testing : Coborn's Central Support Pharmacy : New Trading Partner Setup | Coborn's Central Support Pharmacy | Coborn's Central Support Pharmacy | 11.4.21 Reach out to Charlie for a new contact 10.27.21 No Contacts | 2021-12-20 | No Contacts
Testing : Cosma - Bowling Green Metalforming : New Trading Partner Setup | Cosma - Bowling Green Metalforming | Cosma - Bowling Green Metalforming | 11.4.21 Waiting for new contact from Brandon 10.25.21 Reach out to Cosma for details again:3 10.17.21 Reach out to Cosma for details again:2 10.8.21 Reach out to Cosma for details again 9.29.21 Wait for reply from Cosma 9.26.21 Reach out to Brandon and confirm again 9.22.21 Reach out to new contact:2 9.10.21 Reach out to new contact 9.3.21 Reach out to Brandon Jones for a new Contact 8.27.21 Reach out to trading partner | 2021-12-20 | jana.iddings@magna.com
Testing : Full Compass : New Trading Partner Setup | Full Compass | Full Compass | 11.4.21 Reach out to trading partner | 2021-12-20 | compliance@dicentral.com
Testing : Herregan Distributors Inc. : New Trading Partner Setup | Herregan Distributors Inc. | Herregan Distributors Inc. | 11.4.21 Waiting for the updates for connection methods 10.25.21 Waiting for reply for TP 10.18.21 Reach out to trading partner: 2 10.9.21 Reach out to trading partner: 1 | 2021-12-20 | dgartman@gartman.com
Testing : Home Depot Pro : New Trading Partner Setup | Home Depot Pro | Home Depot Pro | 11.4.21 Reach out to new contact:1 10.25.21 Reach out to Jodi for a new contact | 2021-12-20
Testing : Magna Closures : New Trading Partner Setup | Magna Closures | Magna Closures | 11.4.21 Reach out to trading partner | 2021-12-20 | Everardo.Rodriguez@magna.com
Testing : Peg Perego : New Trading Partner Setup | Peg Perego | Peg Perego | 11.4.21 Reach out to trading partner | 2021-12-20 | mike.palmer@pegperego.com
Testing : Quadratec Vendor : New Trading Partner Setup | Quadratec Vendor | Quadratec Vendor | 11.4.21 Reach out to trading partner | 2021-12-20 | andrew.basenfelder@quadratec.com
Testing : Thoroughbred Diesel : New Trading Partner Setup | Thoroughbred Diesel | Thoroughbred Diesel | 11.4.21 Reach out to trading partner | 2021-12-20 | cody@viduus.org
Testing : Tower Automotive - Bellevue : New Trading Partner Setup | Tower Automotive - Bellevue | Tower Automotive - Bellevue | 11.4.21 Reach out to trading partner: 3 10.25.21 Waiting for updates from Trading partner 10.16.21 Reach out to trading partner: 1 | 2021-12-20 | kseibel@autokiniton.com
Testing : Trenton Cold Storage : New Trading Partner Setup | Trenton Cold Storage | Trenton Cold Storage | 11.4.21 Reach out to Lori for a new contact 10.26.21 Reach out to new contact:3 10.19.21 Reach out to new Contact:2 10.8.21 Reach out to new Contact 9.28.21 Reach out to IM Lori Stevens for a new contact:3 9.22.21 Reach out to IM Lori Stevens for a new contact:2 9.15.21 Reach out to IM Lori Stevens for a new contact 9.6.21 Reached out to trading partner:3 8.27.21 Reached out to trading partner:2 8.20.21 Reached out to trading partner | 2021-12-20
Testing : Uppa Baby : New Trading Partner Setup | Uppa Baby | Uppa Baby | 11.4.21 Reach out to trading partner | 2021-12-20 | brian@uppababy.com
Testing : Valley Bakers : New Trading Partner Setup | Valley Bakers | Valley Bakers | 11.4.21 Reach out to Hirono for the details from customer 10.25.21 Reach out to trading partner:2 10.16.21 Reach out to trading partner: 1 | 2021-12-20 | Mike.Smith@valleybakers.com
Testing : Windsor Modules : New Trading Partner Setup | Windsor Modules | Windsor Modules | 11.4.21 Reach out to trading partner | 2021-12-20 | Stephan.Henze@ajiwin.com
Testing : Cymbio : New Trading Partner Setup | Cymbio | Cymbio | 11.4.21 Reach out to trading partner | 2021-12-20
Testing : Georges Music XML : New Trading Partner Setup | Georges Music XML | Georges Music XML | 11.5.21 Reach out to Aaron for help 10.28.21 Reach out to customer:1 10.20.21 waiting for contact from jodi 10.11.21 Reach out to trading partner: 1 | 2021-12-20 | No Contacts
Testing : Lear Montgomery AL : New Trading Partner Setup | Lear Montgomery AL | Lear Montgomery AL | 11.5.21 Reach out to Lori for a new contact 10.27.21 No Contacts | 2021-12-20 | No Contacts
Testing : Magna Seating Vendor : New Trading Partner Setup | Magna Seating Vendor | Magna Seating Vendor | 11.5.21 Reach out to trading partner | 2021-12-20 | Multiple Records
Testing : Malouf : New Trading Partner Setup | Malouf | Malouf | 11.5.21 Reach out to Lee for a new contact 10.27.21 No Contacts | 2021-12-20 | No Contacts
Testing : Robertson : New Trading Partner Setup | Robertson | Robertson | 11.5.21 Reach out to trading partner | 2021-12-20 | Multiple Records
Testing : Pure Country West : New Trading Partner Setup | Pure Country West | Pure Country West | 11.5.21 Reach out to Miguel for updates 10.29.21 Reach out to Bill again 10.22.21 Reach out to Bill agian 10.15.21 Reach out to Bill agian 10.8.21 Reach out to Bill again 9.28.21 Waiting for reply from Bill 9.22.21 Reach out to trading partenr:2 9.13.21 Reach out to trading partner | 2021-12-20 | rebeccab@purecountry.com
Testing : Stego Germany : New Trading Partner Setup | Stego Germany | Stego Germany | 11.8.21 Assign a mapping case: 13987661 10.28.21 Reach out to Stego for the EDIfact samples 10.21.21 Waiting for trading partner's reply 10.11.21 Reach out to trading partner: 1 | 2021-12-20 | ddeschner@Stego.de
Testing : Del Mar Fans : New Trading Partner Setup | Del Mar Fans | Del Mar Fans | 11.8.21 Assign a mapping case: 13987765 10.29.21 Waiting for the reply 10.20.21 Reach out to trading partner: 2 10.11.21 Reach out to trading partner: 1 | 2021-12-20 | AshleyD@delmarfans.com
Testing : Guitar Center - XML Trading Partner : New Trading Partner Setup | Guitar Center - XML Trading Partner | Guitar Center - XML Trading Partner | 11.8.21 Reach out to Aaron for help 10.29.21 Reach out to new contact 10.21.21 Wait for new contact from Jodi 10.11.21 Reach out to trading partner: 1 | 2021-12-20 | gc@gc.com
Testing : Rhenus Contract Logistics - VSC : New Trading Partner Setup | Rhenus Contract Logistics - VSC | Rhenus Contract Logistics - VSC | 11.8.21 Waiting for contacts from Brad 10.30.21 Wait for updates from Brad 10.21.21 Reach out to Brad for a contact and updates 10.11.21 Reach out to trading partner: 1 | 2021-12-20 | No Contacts
Testing : Wormser Corporation-Jaguar Freight XML : New Trading Partner Setup | Wormser Corporation-Jaguar Freight XML | Wormser Corporation-Jaguar Freight XML | `10.29.21 Reach out to Armin for samples 10.20.21 Waiting for XML sampls and solve of FTP login 10.9.21 Reach out to trading partner: 1 | 2021-12-20 | annmarie@wormsergroup.com | Armin@jaguarfreight.com
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE! |  | 2021-12-20
| #VALUE! | #VALUE!
| #VALUE! | #VALUE!

## notes
SOPI: Pick and pack SOIP: Standard SOI: Pick and Pack No Pack SOTPI: Pallet Pick and Pack SOITP: Pallet Standard
https://network.truecommerce.com:5743/invoke/wm.EDIINT/receive
Neele-vat PO ACK test
I am still waiting for your EDI information to start setup on my end. Whenever you have a chance, could you help me provide following EDI information?
\\Truecommerce.com\data\Corp\Departments\Professional Services\TPS\TPS Documentation
12.20.21
#VALUE!

## Sheet2
NS text | Log ID | Burlington Coat Factory Unknown | Sender name | Transaction type | Receiver name
Error: Burlington Coat Factory Unknown To Unknown LogId 1050778398 | 1050778398 | Burlington Coat Factory Unknown | #NAME? | #NAME? | Unknown
Error: Burlington Coat Factory Unknown To Unknown LogId 1050778399 | 1050778399 | Burlington Coat Factory Unknown | #NAME? | #NAME? | Unknown
Error: Burlington Coat Factory Unknown To Unknown LogId 1050778400 | 1050778400 | Burlington Coat Factory Unknown | #NAME? | #NAME? | Unknown
Error: Burlington Coat Factory Unknown To Unknown LogId 1050778401 | 1050778401 | Burlington Coat Factory Unknown | #NAME? | #NAME? | Unknown
Error: Burlington Coat Factory Unknown To Unknown LogId 1050778402 | 1050778402 | Burlington Coat Factory Unknown | #NAME? | #NAME? | Unknown
Error: Burlington Coat Factory Unknown To Unknown LogId 1050778403 | 1050778403 | Burlington Coat Factory Unknown | #NAME? | #NAME? | Unknown
Error: Burlington Coat Factory Unknown To Unknown LogId 1050778404 | 1050778404 | Burlington Coat Factory Unknown | #NAME? | #NAME? | Unknown
Error: Burlington Coat Factory Unknown To Unknown LogId 1050778405 | 1050778405 | Burlington Coat Factory Unknown | #NAME? | #NAME? | Unknown
Error: Burlington Coat Factory Unknown To Unknown LogId 1050778406 | 1050778406 | Burlington Coat Factory Unknown | #NAME? | #NAME? | Unknown
Error: Burlington Coat Factory Unknown To Unknown LogId 1050778407 | 1050778407 | Burlington Coat Factory Unknown | #NAME? | #NAME? | Unknown
Error: Burlington Coat Factory Unknown To Unknown LogId 1050778408 | 1050778408 | Burlington Coat Factory Unknown | #NAME? | #NAME? | Unknown
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | #NAME? | #VALUE!
#NAME?
#NAME?
#NAME?

## Sheet5
PSA Task Name
Testing : Bioplus Specialty Pharmacy : New Trading Partner Setup
Testing : C2wireless SPS Vendor : New Trading Partner Setup
Testing : Cameron Ashley Building Products, Inc. : New Trading Partner Setup
Testing : CJ Pony Parts - File Partner : New Trading Partner Setup
Testing : Coborn's Central Support Pharmacy : New Trading Partner Setup
Testing : Cosma - Bowling Green Metalforming : New Trading Partner Setup
Testing : Cymbio : New Trading Partner Setup
Testing : Del Mar Fans : New Trading Partner Setup
Testing : Full Compass : New Trading Partner Setup
Testing : Georges Music XML : New Trading Partner Setup
Testing : Guitar Center - XML Trading Partner : New Trading Partner Setup
Testing : Herregan Distributors Inc. : New Trading Partner Setup
Testing : Home Depot Pro : New Trading Partner Setup
Testing : Lear Montgomery AL : New Trading Partner Setup
Testing : Magna Closures : New Trading Partner Setup
Testing : Magna Seating Vendor : New Trading Partner Setup
Testing : Malouf : New Trading Partner Setup
Testing : Peg Perego : New Trading Partner Setup
Testing : Pure Country West : New Trading Partner Setup
Testing : Quadratec Vendor : New Trading Partner Setup
Testing : Raynor Gaming : New Trading Partner Setup
Testing : Rhenus Contract Logistics - VSC : New Trading Partner Setup
Testing : Robertson : New Trading Partner Setup
Testing : Stego Germany : New Trading Partner Setup
Testing : Thoroughbred Diesel : New Trading Partner Setup
Testing : Tower Automotive - Bellevue : New Trading Partner Setup
Testing : Trenton Cold Storage : New Trading Partner Setup
Testing : Uppa Baby : New Trading Partner Setup
Testing : Valley Bakers : New Trading Partner Setup
Testing : Windsor Modules : New Trading Partner Setup